## Product Backlog
ID | User Story
1 | a user should be able to log in
2 | a user should be able to view schedule
3 | a user should be able to view transportaion schedule
4 | A user should have schedule for upcoming exams
5 | A user should be able to offer his schedule for switching
6 | As a user I should be able to switch proctoring schedule with a colleague
7 | As a user I should be able to view my groups' free slots in their Faculties
8 | As a user I should be able to view my hours spent per day for my current schedule
9 | As a user I should be able to receive notifications for my meetings with my professors
10 | As user I should be able to access schedule of courses and staff
11 | As a user I should be able to enter my students' grades for the quizzes and projects
12 | A user should be able to view grades of courses as coursework
13 | A user should be able to view grades of previous semesters
14 | a user should be able to view file grade
15 | a user should be able to post links for submissions
16 | A user should be able to submit assignments
17 | A user should be able to view his transcript
18 | a user should be able to access Faculties methods details
19 | a user should be able to choose best (x out f y) in Faculties method
20 | ------a user should be able to view faculties of courses
21 | a user should be able to manage midterm/final grades
22 | a user should be able to manage group grades
23 | a user should be able to add bonus
24 | A user should be able to download his transcript
25 | A user should be able to know his ranking
26 | A user should get notified when a grade is posted /updated
27 | A user should be able to register for remarking
28 | a user should be able to evaluate the courses
29 | a user should be able to evaluate the professors
30 | a user should be able to evaluate TAs
31 | -----as a user I should be able to view student's max credit hours per semester
32 | A user should be able to evaluate a course
33 | A user should be able to evaluate JTAs
34 | A user should be able to view his performance(evaluation)
35 | A user should be able to view exam statistics per question
36 | a user should be able to view exam attendance statistics
37 | As a user I should be able to view statistics of questions in quizzes
38 | A user should be able to send anonymous tips to instructors
39 | A user should be able to recieve annonymous tips
40 | a user should be able to view their own bachelor journal
41 | a user should be able to view their own phd that they supervised
42 | a user should be able to view their own masters that they supervised
43 | a user should be able to submit progress reports electronically
44 | a user should be able to view past progress reports
45 | a user should be able to search past progress reports
46 | a user should be able to check the list of bachelor students
47 | a user should be able to check the list of phd students
48 | a user should be able to check the list of masters students
49 | a user should be able to search the bachelor journal for other professors
50 | a user should be able to search phd
51 | a user should be able to search masters
52 | a user should be able to check students status
53 | a user should be able to get notified before password expiration
54 | As a user I should be able to change my password
55 | As a user I should be able to report to the IT department any malfunctions
56 | a user should be able to regsiter for a replacement id
57 | A user should be able to register for registeration certificate
58 | a user should be able to register for Wi-Fi
59 | A user should be able to switch major
60 | As a user I should be able to apply on vacation for a certain day
61 | A user should be able to register for excuses for finals
62 | A user should be able to print an excuse for final exam
63 | A user should be able to register for make up exams
64 | A user should be able to register for improvement exams
65 | A user should be able to register for summer courses
66 | A user should be able to choose elective courses
67 | A user should be able to post internships
68 | A user should be able to subscribe to internships
69 | A user should be able to view available program
70 | A user should be able to renew books from library
71 | A user should be able to view attendence
72 | A user should be able to review his attendnce
73 | A user should be notified on updating absence level for a course
74 | As a user I should be able to select attendence slots per group
75 | A user should be able to review his balance
76 | As a user I should be able to view a list of professors Im working with
77 | As a user I should be able to access a list of students' emails in my groups
78 | As a user I should be able to view which students are a graduating case
79 | As a user I should be able to export attendance sheets as pdf
80 | A user should be able to take attendance for a certain teaching group
81 | A user should be able to ask questions about courses
82 | a user should be able to post course materials
83 | As a user I should be able to send a notification mail to all my group(s)
84 | a user should be able to view a list of Teaching Assistants info working with them
85 | a user should be able to send a notification to teaching assistants
86 | a user should be able to access info about staff
87 | a user should be able to access info about courses
88 | As a user I should be able to view a course prerequisites
89 | A user should be able to view FAQ pages
90 | a user should be able to view the fees for every year
91 | A user should be able to review payment methods
92 | a user should be able to view the semester calender
93 | a user should be able to view the campus map
94 | a user should be able to view the University's policy
95 | a user should be able to view reserved/available rooms per slot
96 | A user should be able to view which rooms are available
97 | a user should be able to reserve a compensation slot
98 | A user should be able to reserve rooms and labs afterhours and overnights
99 | a user should get notified when a compensation is added
100 | As a user I should get notified of deadlines of submitting grades and Facultiess
101 | As a user I should be able to assign office hours on my profile

## Sprint 1 Backlog
ID | User Story
1 | a user should be able to log in
2 | a user should be able to view schedule
3 | a user should be able to view transportaion schedule
4 | A user should have schedule for upcoming exams
5 | A user should be able to offer his schedule for switching
6 | As a user I should be able to switch proctoring schedule with a colleague
7 | As a user I should be able to view my groups' free slots in their Faculties
8 | As a user I should be able to view my hours spent per day for my current schedule
9 | As a user I should be able to receive notifications for my meetings with my professors
10 | a user I should be able to access schedule of courses and staff

## Sprint 1 point estimation
ID | User Story | Story points | Reason
1 | a user should be able to log in | 5 | Biggest one in this sprint
2 | a user should be able to view schedule | 2 | easy task
3 | a user should be able to view transportaion schedule | 2 | easy task
4 | A user should have schedule for upcoming exams | 2 | easy task
5 | A user should be able to offer his schedule for switching | 3 | more difficult task and must check for validity of entered username
6 | As a user I should be able to switch proctoring schedule with a colleague | 3 | more difficult task and must check for validity of entered username
7 | As a user I should be able to view my groups' free slots in their Faculties | 4 | must check validity of the group name
8 | As a user I should be able to view my hours spent per day for my current schedule | 3 | needs some calculation upon request
9 | As a user I should be able to receive notifications for my meetings with my professors | 3 | needs some triggers upon a professor adding any meeting with a TA
10 | a user I should be able to access schedule of courses and staff | 4 | must check validity of the staff name and course name

## Sprint 1 task allocation
ID | User Story | Task | Team Member
1 | a user should be able to log in | create Login page | Reem
|  | create home page - Studnet | Farah
|  | create home page - TA | Akmal
|  | create home page - Professor | Salma
2 | a user should be able to view schedule | create a button | Muhad
3 | a user should be able to view transportaion schedule | create button | Mai
4 | A user should have schedule for upcoming exams | create a button | Reem
5 | A user should be able to offer his schedule for switching | create a button | Farah
6 | As a user I should be able to switch proctoring schedule with a colleague | create a button | Akmal
7 | As a user I should be able to view my groups' free slots in their Faculties | create a button | Salma
8 | As a user I should be able to view my hours spent per day for my current schedule | create a button | Muhad
9 | As a user I should be able to receive notifications for my meetings with my professors | create a button | Mai
10 | a user I should be able to access schedule of courses and staff | create a page for searching for course and staff schedules | Reem

## Sprint 2 Backlog
ID | User Story
1 | As a user I should be able to enter my students' grades for the quizzes and projects
2 | A user should be able to view grades of courses as coursework
3 | A user should be able to view grades of previous semesters
4 | a user should be able to view file grade
5 | a user should be able to post links for submissions
6 | A user should be able to submit assignments
7 | A user should be able to view his transcript
8 | a user should be able to access Faculties methods details
9 | a user should be able to choose best (x out f y) in Faculties method
10 | a user should be able to manage midterm/final grades
11 | a user should be able to manage group grades
12 | a user should be able to add bonus
13 | A user should be able to download his transcript
14 | A user should be able to know his ranking
15 | A user should get notified when a grade is posted /updated
16 | A user should be able to register for remarking
17 | a user should be able to evaluate the courses
18 | a user should be able to evaluate the professors
19 | a user should be able to evaluate TAs
20 | A user should be able to evaluate JTAs
21 | A user should be able to view his performance(evaluation)
22 | A user should be able to view exam statistics per question
23 | a user should be able to view exam attendance statistics
24 | As a user I should be able to view statistics of questions in quizzes
25 | A user should be able to send anonymous tips to instructors

## Sprint 2 Task allocation
ID | User Story | Task | Team Member
1 | As a user I should be able to enter my students' grades for the quizzes and projects | create a page for entering student's id and grade | Reem
2 | A user should be able to view grades of courses as coursework | create a page for grade viewing | Salma
3 | A user should be able to view grades of previous semesters | create a page for choosing previous semesters and previous courses | Muhad
4 | a user should be able to post links for submissions | create a page for posting submission links | Mai
5 | A user should be able to submit assignments | create a page for submitting course work | Reem
6 | A user should be able to view his transcript | create a page for viewing transcript | Farah
7 | a user should be able to access Faculties methods details | create a button that goes to faculties methods | Akmal
8 | a user should be able to choose best (x out f y) in Faculties method | create button to choose best(x out of y) for a course | Muhad
9 | a user should be able to view file grade | create button that goes to file grade | Mai
|  | create page to view file grade of a choosen course | Reem
10 | a user should be able to manage midterm/final grades | create button | Farah
|  | create page to manage grades | Akmal
11 | a user should be able to manage group grades | create button to go to grading page | Salma
|  | create page for managing grades | Muhad
12 | a user should be able to add bonus | create button | Mai
|  | create page to choose bonus | Reem
13 | A user should be able to download his transcript | create "export as pdf" button | Farah
14 | A user should be able to know his ranking | create button | Akmal
15 | A user should get notified when a grade is posted /updated | create button that goes to posted/updated grades | Salma
16 | A user should be able to register for remarking | create button | Muhad
|  | create page to choose exam to remark | Mai
17 | a user should be able to evaluate the courses | create button | Reem
18 | a user should be able to evaluate the professors | create button | Farah
19 | a user should be able to evaluate TAs | create button | Akmal
|  | create page to choose course, professor or TA to review | Salma
20 | A user should be able to view exam statistics per question | create button that goes to statistics page | Muhad
|  | create page to view exam statistics | Mai
21 | a user should be able to view exam attendance statistics | create button | Reem
|  | create page that views exam attendance statistics | Farah
22 | As a user I should be able to view statistics of questions in quizzes | create button | Akmal
|  | create page for statistics viewing | Salma
23 | A user should be able to send anonymous tips to instructors | create button and tesxt boxes to get the tip and the instructor name | Muhad
24 | A user should be able to evaluate JTAs | a page for entering JTA's name and evaluation | Mai
25 | A user should be able to view his performance(evaluation) |  | Reem
26 | A user should be able to recieve annonymous tips |  | Farah

## Sprint 3 Backlog
ID | User Story
1 | a user should be able to view their own bachelor journal
2 | a user should be able to view their own phd that they supervised
3 | a user should be able to view their own masters that they supervised
4 | a user should be able to submit progress reports electronically
5 | a user should be able to view past progress reports
6 | a user should be able to search past progress reports
7 | a user should be able to check the list of bachelor students
8 | a user should be able to check the list of phd students
9 | a user should be able to check the list of masters students
10 | a user should be able to search the bachelor journal for other professors
11 | a user should be able to search phd
12 | a user should be able to search masters
13 | a user should be able to check students status
14 | a user should be able to get notified before password expiration
15 | As a user I should be able to change my password
16 | As a user I should be able to report to the IT department any malfunctions
17 | a user should be able to regsiter for a replacement id
18 | A user should be able to register for registeration certificate
19 | a user should be able to register for Wi-Fi
20 | A user should be able to switch major
21 | As a user I should be able to apply on vacation for a certain day
22 | A user should be able to register for excuses for finals
23 | A user should be able to print an excuse for final exam
24 | A user should be able to register for make up exams
25 | A user should be able to register for improvement exams
26 | A user should be able to register for summer courses
27 | A user should be able to choose elective courses

## Sprint 3 Task Allocation
ID | User Story | Task | Team Member
1 | Changing Password | Create a page for Password Change | Reem
2 | Report to IT malfunctions | Create a page for sending messages to IT | Reem
3 | Switching Major | Create a page for sending requests to change major | Reem
4 | Register for WI-FI | create a page for entering MAC address and phone number | Reem
5 | Change Password | create a page for entering old and new password | Reem
6 | As a user I should be able to apply on vacation for a certain day | Create a page for sending request to have a leave | Farah
7 | a user should be able to check students status | Create a page to view a specific student status | Farah
8 | a user should be able to get notified before password expiration | Create a page to to send a notification to users | Muhad
9 | register for ID | create button | Akmal
10 | Register for registeration certificate | create button | Akmal
11 | Register for final excuse | create page | Akmal
12 | Print excuse form | create button | Akmal
13 | Register for make up exam | create page | Akmal
14 | Register for improvement exam | create page | Akmal
15 | Register for summer course | create page | Akmal
16 | Choose elective courses | create page | Akmal
17 | a user should be able to get notified before password expiration | create an icon for password expiration page | salma
|  | create a page to view expiration date | salma
|  | create an icon for redirection to change password | salma
18 | As a user I should be able to change my password | create a page to change password | salma
19 | As a user I should be able to report to the IT department any malfunctions | create a page for malfunctions report | salma
20 | a user should be able to register for Wi-Fi | create a page for wifi registeration | salma
21 | a user should be able to view their own bachelor journal | create an icon for researchers' portal in the home page | Mai
22 | a user should be able to view their own phd that they supervised | create a page to view/search bachelor journal | Mai
23 | a user should be able to view their own masters that they supervised | create a page to view/search PhDs | Mai
24 | a user should be able to submit progress reports electronically | create a page to view/search masters | Mai
|  | create a page to submit progress reports | Mai
25 | a user should be able to view past progress reports | add an upload button | Mai
26 | a user should be able to search past progress reports | create a page to view past progress reports | Mai
27 | a user should be able to check the list of bachelor students | add a search option in the view past prgress reports page | Mai
28 | a user should be able to check the list of phd students | create a page to display students under supervision | Mai
|  | create an icon for students under supervision in the Phd page | Mai
29 | a user should be able to check the list of masters students | create a page to display students under supervision | Mai
|  | create an icon for students under supervision in the masters page | Mai
30 | a user should be able to search the bachelor journal for other professors | create a page to display students under supervision | Mai
31 | a user should be able to search phd | create a page to search other supervisers' bachelor journal | Mai
32 | a user should be able to search masters | create a page to search other supervisers' phds | Mai
33 | a user should be able to check students status | create a page to search other supervisers' masters | Mai
|  | create a button in the searched bachelor page | Mai
|  | create a page with students statuses | Mai
|  | create a button in the supervised masters page | Mai
|  | create a page with students statuses | Mai
|  | create a button in the supervised PhDs page | Mai
|  | create a page with students statuses | Mai

## Sprint 4 Backlog
ID | User Story
1 | A user should be able to post internships
2 | A user should be able to subscribe to internships
3 | A user should be able to view available program
4 | A user should be able to renew books from library
5 | A user should be able to view attendence
6 | A user should be able to review his attendnce
7 | A user should be notified on updating absence level for a course
8 | As a user I should be able to select attendence slots per group
9 | A user should be able to review his balance
10 | As a user I should be able to view a list of professors Im working with
11 | As a user I should be able to access a list of students' emails in my groups
12 | As a user I should be able to view which students are a graduating case
13 | As a user I should be able to export attendance sheets as pdf
14 | A user should be able to take attendance for a certain teaching group
15 | A user should be able to ask questions about courses
16 | a user should be able to post course materials
17 | As a user I should be able to send a notification mail to all my group(s)
18 | a user should be able to view a list of Teaching Assistants info working with them
19 | a user should be able to send a notification to teaching assistants
20 | a user should be able to access info about staff
21 | a user should be able to access info about courses

## Sprint 4 Task Allocation
ID | User Story | Task | Team Member
1 | access info about courses | create page for searching for the course name | Reem
2 | access info about staff | create page for searching for the staff name | Reem
3 | ask questions about courses | create a text box for submitting the question | Reem
4 | review balance | create a page for viewing financial balance | Reem
5 | subscribe to internships | create page to choose company and position | Akmal
6 | view available programs | create page displaying all majors | Akmal
7 | renew books | create page to renew library book borrowing | Akmal
8 | view attendance | create page to show attendance level | Akmal
9 | absence level notification | create button to redirect to attendance page | Akmal
10 | a user should be able to view a list of Teaching Assistants info working with them | create an option to access teaching assisstants info for each course | Mai
|  | create a page for viewing teaching assisstants info and emails | Mai
11 | a user should be able to send a notification to teaching assistants | create an option to send all teaching assisstants a mail for a certain course | Salma
12 | A user should be able to post internships | create a page to post internships | Salma
13 | As a user I should be able to select attendence slots per group | create a page to view attendence | Farah
14 | As a user I should be able to view a list of professors Im working with | create a page to view professors a user is working with | Farah
15 | As a user I should be able to access a list of students' emails in my groups | create a page to view students' mails | Farah
16 | As a user I should be able to view which students are a graduating case | create a page to view students status | Farah
17 | As a user I should be able to export attendance sheets as pdf | create a button to export attendence sheets | Muhad
18 | A user should be able to take attendance for a certain teaching group | create a page to take students' attendence | Muhad
19 | As a user I should be able to send a notification mail to all my group(s) | create a page to send notification mail to students | Muhad
20 | a user should be able to access info about courses | create a page to view courses info | Muhad

## Sprint 5 Backlog
ID | User Story
1 | As a user I should be able to view a course prerequisites
2 | A user should be able to view FAQ pages
3 | a user should be able to view the fees for every year
4 | A user should be able to review payment methods
5 | a user should be able to view the semester calender
6 | a user should be able to view the campus map
7 | a user should be able to view the University's policy
8 | a user should be able to view reserved/available rooms per slot
9 | A user should be able to view which rooms are available
10 | a user should be able to reserve a compensation slot
11 | A user should be able to reserve rooms and labs afterhours and overnights
12 | a user should get notified when a compensation is added
13 | As a user I should get notified of deadlines of submitting grades and Facultiess
14 | As a user I should be able to assign office hours on my profile

## Sprint 5 Task Allocation
ID | User Story | Task | Team Member
1 | As a user I should be able to view a course prerequisites | page for searching for courses | Reem
2 | A user should be able to view FAQ pages | page for viewing FAQs | Reem
3 | a user should be able to view the fees for every year | page for viewing fees | Reem
4 | A user should be able to review payment methods | page for viewing payment methods | Reem
5 | a user should be able to view the semester calender | page for semester Calendar | Reem
6 | As a user I should be able to view a course prerequisites | page for viewing courses prerequisites | Farah
7 | a user should be able to view the semester calender | page for viewing semester calendar | Farah
8 | a user should be able to view the campus map | page for viewing campus map | Farah
9 | a user should be able to view the University's policy | page for viewing university policy | Farah
10 | a user should be able to view reserved/available rooms per slot | page for viewing available or reserved rooms | Farah
11 | A user should be able to view which rooms are available | page for viewing available rooms | Muhad
12 | a user should be able to reserve a compensation slot | page for reserving compensation slot | Muhad
13 | As a user I should get notified of deadlines of submitting grades and Facultiess | page for viewing submission notifications | Muhad
14 | As a user I should be able to assign office hours on my profile | page for selecting and displaying office hours | Muhad
15 | a user should be able to view the campus map | page showing the map | Akmal
16 | a user should be able to view the University's policy | page showing the policy | Akmal
17 | A user should be able to reserve rooms and labs afterhours and overnights | page for choosing date and time and room | Akmal
18 | a user should get notified when a compensation is added | button to go to calender | Akmal
19 | As a user I should get notified of deadlines of submitting grades and Facultiess | button to go to calender | Akmal